Brandeston Parish Plan – Steering Group  Meeting Minutes – 16/08/2007

Venue:	Brandeston Village Hall

Present:

Nick Holland-Brown

Alastair Chapman

Graham Edhouse

Annie Law

Peter Thurlow

Nick Hayward

# Item 1 -  Apologies:

Paddy Fielder, David Fletcher, Laurie Moody, Henrietta Rogers, Sarah Thorne.

# Item 2 -  Minutes of  Previous Meeting

Accepted.

# Item 3 -  Matters Arising

PT confirmed his acceptance of the role of Publicity Officer.

Henrietta Rogers is to be co-opted on to the Steering Committee.

NHB confirmed that SCDC Planning Department reps would be prepared to visit Brandeston. for the next meeting to explain Core Strategies.

# Item 4 -  Action Plan review

## Steering Group – Objectives and ToRs

Draft approved and authorised for circulation to PC.

## Budget and funding application

DEFRA funding was likely to dry up by the end of March ’08 so the application was required quickly.  AC presented draft budgets for discussion and version 1.3, together with timeline and cashflow, was accepted, subject to review of cost of printing/binding final report.

## Timeline

Draft accepted; to be copied to PC.  It was emphasised that opportunity must be made for all in the village to contribute to the end report.  This would be achieved by a questionnaire and open debate where, for example, early conclusions could be presented for public discussion to sweep up outstanding issues.	 Consequently the timeline should be regarded as a guide and remain flexible.

## Questionnaire

An initial draft of 2 pages was tabled for discussion, based on the Long Melford model.  The principle was agreed and a full draft was to be circulated to the Steering Group by email ahead of the next meeting.

## Existing plans

Carried forward.

## Stakeholders

Carried forward.  Identify and consult stakeholders and allow them to state personal views.  Check on website how Long Melford dealt with this group.

# -  Actions

Pass agreed Project Objective and Terms of Reference (ToRs) to the PC.            ACTION NH

Confirm a meeting with the Planning Department for next meeting.	          ACTION NHB

Check if P. Council has any plans/strategies that should be considered.       ACTION PF (C/F)

List contacts (stakeholders) to be involved in consultation (eg Brandeston Hall, Queen’s Head PH, tourists at the pub).							 ACTION ALL (C/F)

Draft project budget and funding application, to include printing, distribution, social events, etc by time of next PC meeting in September. Review cost of printing/binding final report and submit under covering letter to David Risk/Mark Hounsell on the PC.	            ACTION AC

Draft Questionnaire to be circulated by email before 18/9 meeting.	      ACTION AC/NH

Review Long Melford website regarding how stakeholders were consulted.           ACTION AL

# Item 5 -  AOB

None.

# Item 6 -  Date of Next Meeting

Tuesday 18 September 2007, 8.00pm, Brandeston Village Hall, followed by

Wednesday 10 October, 8.00pm.

Nick Hayward, 19/08/2007