Brandeston Parish Plan – Steering Group  Meeting Minutes – 22/11/2007

Venue:	Brandeston Village Hall

Present:

Nick Holland-Brown

Alastair Chapman

Roger Cunliffe

Annie Law

Phil Summers

Peter Thurlow

Nick Hayward

# Item 1 -  Apologies:

Clemency Cunliffe, Henrietta Rogers, Wilda Woodland

Note, Hetta Rogers is likely to working away for the foreseeable future.

# Item 2 -  Minutes of  Previous Meeting

Accepted.

# Item 3 – Matters arising

Actions from last meeting completed except for those carried forward, see below, and withdrawal of the proposal to seek review of questionnaire through the Coffee Morning .

# Item 4 – Budget & funding application

Suffolk ACRE (SA) had commented at the end of October on the application, accepting its overall value but requesting that it be re-balanced so that £300 were allocated to data collection and less were spent on the final report which should be limited to 30 formal full copies with electronic versions and summaries made available via the web and provided to SA (which we had intended to do).  Also, Brandeston would need to show evidence of consultation with stakeholders.  AC had since spoken to Jon Bell of SA regarding the re-balance but pointing out that some consultation letters had been written already and others would be initiated as the project progressed – see also item 6, below.  AC tabled a revised version of the budget which was agreed.

AC agreed to confirm the budget to JB of SA and seek approval to proceed.

# Item 5 – Questionnaire

NHB asked to record his thanks for NH’s work on the Questionnaire and the analysis tool which have been prepared.

## Analysis

NH demonstrated a proposed process in outline of how the data from the questionnaires should be collected and analysed using a series of spreadsheets which, in principle, was accepted.  The key to this process being successful in terms of integrity would be disciplined issue and collection of the questionnaires and careful keying of the data.

It was thought that geographical grouping of questionnaires would allow localised issues to be highlighted without compromising anonymity.

## Distribution/collection

A careful plan of collectors and geographical groupings of addresses was required ahead of distribution.  Issue of the questionnaire in an envelope with cloakroom ticket attached would allow the collector to ensure that the correct respondents were received and these could be entered into the incentive draw.

The `flyer’ would be issued 2 weeks ahead of the main questionnaire.

Before going on holiday, PF had agreed to organise and coordinate the distribution/collection process, subject to briefing.

# Item 6 – Consultation Process

NHB had written to a number of stakeholders (list provided, but including SCC, SCDC) and agreed to make further contacts (eg to adjoining parishes, bus company, Environment Agency, utilities, emergency services, pub, school, user groups, Suffolk Wildlife Trust), given a suitable draft letter which RC volunteered to provide.  This will provide SA with evidence that the process has been undertaken.  AC to provide addresses by email to NHB.

# Item 7 – Revised timeline

The project has been on hold awaiting approval of the budget.  A revised timeline for the project is attached at Appendix A showing the impact.  It assumes budget approval by end November ’07.

# Actions

Seek urgent budget approval from Jon Bell of Suffolk ACRE.		            ACTION AC

Draft stakeholder `Consultation’ letter.						ACTION RC

Continue initiating consultation with stakeholders.			          ACTION NHB

Provide stakeholder addresses via email to NHB.		  		ACTION AC

Brief PF on questionnaire distribution process.					ACTION NH

Organise/coordinate flyer and questionnaire distribution/collection.		ACTION PF

List contacts (stakeholders) to be involved in consultation (eg Brandeston Hall, Queen’s Head PH, tourists at the pub).							 ACTION ALL (C/F)

Draft visitors’ questionnaire sheet.			             	   ACTION AC (C/F)

# Item 8 – AOB

None.

# Item 9 -  Date of Next Meeting

Thursday 13 December 2007,  8.00pm, Brandeston Village Hall.

Nick Hayward 24/11/2007

# Appendix A – Revised Timeline